## assistant-app
Assistant app
Add your board's description here
This month
Name | Subitems | Person | Status | Date
Project 1 ( template of app / Navigation between screens) | 1# Create Logo, 2# Create A navigation Bar(functioning), 3# Create all the Required Screens using the template Created. | Amir Mohamed | Working on it | 2023-03-25
Subitems | Name | Owner | Status | Date
1# Create Logo
2# Create A navigation Bar(functioning)
3# Create all the Required Screens using the template Created.
Project 2 ( Designing/ Implementing features 1- 3 & HomeScreen) | 2# Create the design For Calendar Feature, 1# Create A Login Screen (Forgot P/Create Acc), 3# Create the Design For Reminder Feature, 4# Create the Design For Note Feature |  | Working on it | 2023-04-05
Subitems | Name | Owner | Status | Date
1# Create A Login Screen (Forgot P/Create Acc)
2# Create the design For Calendar Feature
3# Create the Design For Reminder Feature
4# Create the Design For Note Feature
Project 3 ( Design / implement features) | 1# Implement Functions Into Login Feature, 2# Implement Functions Into Calendar Feature, 3# Implement Functions Into Reminder Feature, 4# Implement Functions Into Note Feature, 5#Design the home screen Include miniature Features of the implemented Features |  | Working on it | 2023-04-10
Subitems | Name | Owner | Status | Date
1# Implement Functions Into Login Feature
2# Implement Functions Into Calendar Feature
3# Implement Functions Into Reminder Feature
4# Implement Functions Into Note Feature
5#Design the home screen Include miniature Features of the implemented Features
Project 4 (Design/Implementing ) | 1# Make Final Adjustments to the Developed part of the project(fixes/improvements), 2# Start designing the Budgeig Feature, 3# Implement function into the budgeting feature, 4# Adjust the budgeting design / functions, 5# Create a way to interact to the budgeting feature in the home screen |  | Working on it | 2023-04-20
Subitems | Name | Owner | Status | Date
1# Make Final Adjustments to the Developed part of the project(fixes/improvements)
2# Start designing the Budgeig Feature
3# Implement function into the budgeting feature
4# Adjust the budgeting design / functions
5# Create a way to interact to the budgeting feature in the home screen
Proect 5(Final Check of Interface/Feature) (TESTING) | 1# Test Interface Design & Calendar Feature, 2# Test Interface Design & Reminder Feature, 3# Test Interface Design & Note Feature, 4# Test Interface Design & Budgeting Feature, 5# Test Interface Design & Home Screen Features |  | Working on it | 2023-04-22
Subitems | Name | Owner | Status | Date
1# Test Interface Design & Calendar Feature
2# Test Interface Design & Reminder Feature
3# Test Interface Design & Note Feature
4# Test Interface Design & Budgeting Feature
5# Test Interface Design & Home Screen Features
2023-03-25 to 2023-04-22